## Instructions
Supplier Qualification Toolkit
Built by Sylvia Wanjiru Opiyo, Operational Excellence & Quality Leader
HOW TO USE THIS TOOLKIT
This is a lightweight, PPAP-inspired process for qualifying a new supplier or component,
built for teams that need to move fast (often with engineering outsourced overseas) without
losing track of the specs that actually matter once the product meets real-world use.
1. Go to 'Specs Register'. List every requirement you're checking for. Mark the ones that
matter most given how the product will actually be used, not just what a standard spec
sheet assumes. Delete the example row before adding your real specs.
2. Go to 'Milestone Tracker'. This is your big-picture view: seven stages from first
agreement to final sign-off, including a Screen stage before you invest in a sample run.
Update the Status column as you progress. % Complete updates on its own.
3. Every time the supplier sends a new batch or sample, open 'Batch Log', fill in that
round's date, and mark each spec Pass, Partial, or Fail. Watch for a cell with a bold red
border: that means something PASSED in an earlier batch and just failed again. That's a
stronger warning sign than a first-time failure. It usually means there's no real process
control on the supplier's side, just manual firefighting of whatever was flagged last time.
4. Once a supplier is qualified, the work isn't over. Review 'Performance Scorecard' on a
set cadence, quarterly is common, scoring Quality, Delivery, Responsiveness,
Documentation, and Cost. Overall Score and Status calculate automatically. This is what
catches a supplier drifting after they've already been locked in.
5. Use 'Collaboration Log' to track the relationship side: joint calls, issues the supplier
fixed proactively, agreements reached. This is what turns a vendor into a partner, and
it's easy to forget once you're deep in spec details.
6. Check 'Executive Summary' whenever you need a fast answer to "how far along are we, and
is this still worth it": overall progress, how many rounds and months this has taken,
how many regressions have happened, and the supplier's latest performance status.
SHARING THIS WITH YOUR SUPPLIER
Many suppliers, especially in mainland China, don't have reliable access to live Google
Sheets links. The workflow that actually works in practice: download this as an Excel file
(File > Download > Microsoft Excel), send it to your supplier contact by email or WeChat.
They fill in what they've changed on their end and send it back. You review it, add your own
notes directly into the same file for what still needs work, and send it back again. Repeat
each round.
This keeps one continuous, unambiguous document trail both sides can point back to. Neither
side can later claim the information was vague or unfair, since every round is right there in
the same file, in order.
For a quick visual update to share over WeChat without sending the whole file, print just
the tab you want (File > Print, select current sheet only) and save it as a PDF.
This toolkit is a directional tool, not a certification. For regulated or safety-critical
parts, a full formal PPAP process with your quality team is still the right call.

## Executive Summary
Executive Summary
Auto-updates from the Milestone Tracker and Batch Log. Use this view for a fast go/no-go conversation.
Overall milestone progress | 0% | Pulled directly from the Milestone Tracker tab.
1
Total specs tracked | 1 | Counts real specs entered (excludes the example row).
First round logged | Not started | Earliest Round Date filled in on the Batch Log.
Most recent round logged | Not started | Latest Round Date filled in on the Batch Log.
Approx. time elapsed (months) | 0 | Rounded from first to most recent round date.
Total regressions detected | 0 | Every time a spec passed, then failed or went partial in a later round.
Latest performance status | Performing | Pulled from the most recent row in Performance Scorecard. Review that tab on a set cadence, not just when something breaks.
For the current status of any individual spec, see the Batch Log tab. This summary is directional, meant to support a fast decision, not replace looking at the detail when it matters.
For the current status of any individual spec, see the Batch Log tab. This summary is directional, meant to support a fast decision, not replace looking at the detail when it matters.

## Specs Register
Spec ID | Spec / Requirement | Critical for real-world use? | Target Value | Date Added | Notes / Rationale
1 | Example: Frame weld strength holds under 120kg dynamic load | Y | No visible crack after 10,000 load cycles | 2026-01-15 | Delete this row before adding your real specs

## Milestone Tracker
Stage | Status | Owner | Date Started | Date Completed | Notes / Evidence
1. Spec & Design Agreement
2. Supplier Screened
3. Initial Sample Submitted
4. Sample Validated
5. Process Consistency Proven
6. Open Issues Resolved
7. Final Approval / Sign-off
Overall % Complete | 0%
Any stage blocked? | No

## Batch Log
Spec | Batch 1 | Batch 2 | Batch 3 | Batch 4 | Batch 5 | Batch 6 | Batch 7 | Batch 8
Round Date
Example: Frame weld strength holds under 120kg dynamic load
Legend: Green = Pass, Amber = Partial, Red = Fail. A bold red border means REGRESSION: this passed in an earlier batch and just failed again.
Fill in Round Date each time you log a batch. Need more than 8 rounds? Insert a column, copy the formatting, and extend the regression rule.

## Performance Scorecard
Period | Supplier | Quality | Delivery | Responsiveness | Documentation | Cost / Commercial | Overall Score | Status | Review Action
Q1 2026 | Example: Rim supplier | 4 | 4 | 5 | 3 | 4 | 4 | Performing | Delete this row before adding your real reviews
Score each category 1 (poor) to 5 (excellent). Overall Score and Status calculate automatically. Review on a set cadence, quarterly is common, not just when something goes wrong.

## Collaboration Log
Date | Type | Raised By | Description
2026-01-20 | Proactive Fix | Supplier | Example: Supplier noticed a tolerance drift on their own QC line and flagged it before we found it in Batch 3. Delete this row before logging real entries.